## Summary
Scope Of Services Section | Scope Of Services Language | Consultant's List | Actual Document Title | Files | path | Electronic File | Consultant Fulfillment | Draft Target Date
[8 empty] | Oirignal | Revised
3.2.1 | Kick-off Meeting Agenda and Handout |  |  | Go | 3.2.1 | No
| Meeting Minutes (5 copies) |  |  | Go | 3.2.1 | No
3.3 | Project Procedures Manual (6 copies) | Project Procedures Manual (final, June 2016) | Project Procedures Manual | Go | 3.3 | Yes
| Updates to project procedures |  |  | Go | 3.3
3.4.1 | Initial Project Schedule (6 copies) | Initial Project Schedule (submitted) | Project Procedures Manual | Go | 3.4.1 | Yes
3.4.3 | Monthly Project Status Reports |  | Progress Report | Go | 3.4.3 | Yes
3.5 | Monthly Invoices |  | Invoice | Go | 3.5 | Yes
3.6 | Project Quality Plan (6 copies) | Project Quality Plan (to be submitted as part of the Project Procedures Manual) (final, June 2016) | Project Procedures Manual | Go | 3.6 | Yes
4.1 | Data Management Plan |  |  | Go | 4.1
4.5 | Documentation of CONSULTANT's internal QC review with each submittal |  |  | Go | 4.5
5.3.2 | Technical Memorandum: Risk Analysis & Prioritization of Segments - Three Raw Water Pipelines |  |  | Go | 5.3.2
5.3.3 | Technical Memorandum: Initial Programmatic Risk Assessment |  |  | Go | 5.3.3
5.3.4 | Workshop: Results of Risk Analysis |  |  | Go | 5.3.4
6.1.3 | Technical Memorandums: Geotechnical Hazards & Considerations (one TM for each pipeline) | Technical Memorandums (3): Geotechnical Hazards and Considerations - Raw Water Pipelines | Geotechnical Desktop Study Sutherland Pipeline Condition Assessment | Go | 6.1.3/Sut | Yes
|  |  | Geotechnical Desktop Study San Vicente 1st and 2nd Pipelines Condition Assessment | Go | 6.1.3/SV | Yes
6.1.4 | Technical Memorandum: Corrosion Evaluations (one TM for each pipeline) | Technical Memorandums (3): Corrosion Evaluations - Raw Water Pipelines | Technical Memorandum - City of San Diego Sutherland Pipeline Corrosion Evaluation | Go | 6.1.4/Sut | Yes
|  |  | Technical Memorandum - City of San Diego San Vicente 1st Pipeline Corrosion Evaluation | Go | 6.1.4/SV1 | Yes
|  |  | Technical Memorandum - City of San Diego San Vicente 2nd Pipeline Corrosion Evaluation | Go | 6.1.4/SV2 | Yes
6.2.3 | Field Work Plans | Field Work Plan: Phase 1 Field Inspectoins - Raw Water Pipelines | Field Work Plan - Raw Water Pipelines | Go | 6.2.3/Raw | Yes
|  | Manned Entry Inspection Plan - San Vicente 1 & 2 Raw Water Pipelines | Manned Entry Inspection Plan San Vicente 1 & 2 Raw Water Pipelines | Go | 6.2.3/SVP | Yes
|  | Manned Entry Inspections of the San Vicente Bypass Pipeline | Manned Entry Inspections of the San Vicente Bypass Pipeline | Go | 6.2.3/SVB | Yes
|  | Valve Assessment Work Plan - Raw Water Pipelines | Valve Assessment Work Plan | Go | 6.2.3/Val | Yes
|  |  | Raw Water Valve Assessments Technical Memorandum - Appendix E | Go | 6.2.4 | Yes
6.2.4 | Valve assessment reports | Valve Assessment Report - Raw Water Pipelines | Raw Water Valve Assessments Technical Memorandum | Go | 6.2.4 | Yes
| Work orders for valve repairs by City |  | Raw Water Valve Assessments Technical Memorandum - Appendix H | Go | 6.2.4 | Yes
| Esri ready GIS files |  | Raw Water Valve Assessments Technical Memorandum - Appendix G | Go | 6.2.4 | Yes
| Valve database (minimum 33 data points per valve, developed exclusively for this project) for inclusioin in SPLASH or ArcGIS |  | Raw Water Valve Assessments Technical Memorandum - Appendix H | Go | 6.2.4 | Yes
Amd 1 6.2.9 | Draft and Final Condition Assessment Reports (one report for each pipeline) |  |  | Go | 6.2.9
| Field data and inspection results formatted and compiled for inclusion in SPLASH or ArcGIS |  |  | Go | 6.2.9
6.2.10 | Workshop: Post-Field Inspection Reporting - Phase 1 Field Assessments (Including Results of Valve Assessments) |  |  | Go | 6.2.10
| Workshop: Post-Field Inspection Reporting - Phase 2 Field Assessments |  |  | Go | 6.2.10/Ph2
Amd 1 6.4.2 | DRAFT Reports (5 copies) | Draft Condition Assessment Reports (3) - Raw Water Pipelines | Condition Assessment Report: Sutherland Raw Water Pipeline | Go | 6.4.2/Sut
|  |  | Condition Assessment Report: San Vicente Raw Water Pipeline No. 1 | Go | 6.4.2/SV1
|  |  | Condition Assessment Report: San Vicente Raw Water Pipeline No. 2 | Go | 6.4.2/SV2
| FINAL Reports (8 copies) | Final Condition Assessment Reports (2) - Raw Water Pipelines | Condition Assessment Report: Sutherland Raw Water Pipeline | Go | 6.4.2/Sut
|  |  | Condition Assessment Report: San Vicente Raw Water Pipeline No. 1 | Go | 6.4.2/SV1
|  |  | Condition Assessment Report: San Vicente Raw Water Pipeline No. 2 | Go | 6.4.2/SV2
6.4.3 | Workshop: Presentation of Reports |  |  | Go | 6.4.3
7.1.3 | Technical Memorandum: Soil Resistivity Test Results (one TM for all pipelines) | Technical Memorandum: Soil Resistivity Test Results - Potable Water Pipelines | Technical Memorandum - City of San Diego 31 Potable Water Pipelines - Soil Corrosivity Evaluation | Go | 7.1.3 | Yes
7.1.4 | Technical Memorandum: Geotechnical Hazards & Considerations (City-Wide) | Technical Memorandum: Geotechnical Hazards and Considerations (City-Wide) Potable Water Pipelines |  | Go | 7.1.4
7.1.5 | Technical Memorandum: Environmental Evaluation of Potable Water Transmission Pipeline Alignments | Technical Memorandum: Environmental Evaluation of Potable Water Transmission Pipeline Alignments |  | Go | 7.1.5
7.1.7 | Technical Memorandum: Prioritization of Pipe Segments and Recommendations for Detailed Pipeline Inspection and Condition Assessments | Technical Memorandum: Prioritization of Pipe Segments and Recommendations for Detailed Pipeline Inspection and Condition Assessments |  | Go | 7.1.7
7.1.8 | Workshop: Final Prioritization of Pipe Segments |  |  | Go | 7.1.8
7.2.3 | Field Work Plans | Valve Assessment Work Plan - Potable Water Pipelines | Potable Water Valve Assessments Work Plan | Go | 7.2.3/Val | Yes
|  | Field Work Plan: Phase 1 Field Inspectoins - Potable Water Pipelines | CCTV Inspection Field Work Plan - Potable Water Pipelines | Go | 7.2.3/Ctv | Yes
7.2.4 | Valve assessment reports | Valve Assessment Report - Potable Water Pipelines |  | Go | 7.2.4
| Work orders for valve repairs by City |  |  | Go | 7.2.4
| Esri ready GIS files |  |  | Go | 7.2.4
| Valve database (minimum 33 data points per valve, developed exclusively for this project) for inclusioin in SPLASH or ArcGIS |  |  | Go | 7.2.4
7.2.5 | Report by Wachs Water Services of Video and Leak Detection Inspection Results and video inspection screen shots (data) for inclusion in City's GIS |  |  | Go | 7.2.5
7.2.6 | Potable Technical Memorandums: Geotechnical Hazards & Considerations (one TM for each pipeline) |  |  | Go | 7.2.6
7.2.7 | Technical Memorandums: Results of Non-Destructive Testing (one TM for each pipeline) |  |  | Go | 7.2.7
7.2.8.1 | Technical Memorandums: Interpretation of Laboratory Analysis of Soil Samples |  |  | Go | 7.2.8.1
7.2.9 | Workshop: Post-Field Inspection Reporting - Phase 1 Field Assessments (Including Results of Valve Assessments) |  |  | Go | 7.2.9
| Workshop: Post-Field Inspection Reporting - Phase 2 Field Assessments |  |  | Go | 7.2.9
7.4.3 | DRAFT Final Programmatic Transmission Pipeline Risk Assessment Analysis and Pipeline Replacement Program Report (5 copies) |  |  | Go | 7.4.3
| FINAL Final Programmatic Transmission Pipeline Risk Assessment Analysis and Pipeline Replacement Program Report (8 copies) |  |  | Go | 7.4.3
| Field inspection data formatted for inclusion in City's SPLASH/Smallworld GIS or ArcGIS system |  |  | Go | 7.4.3

## Parameters
Deliverable Files Directory | Files